FORWARD DEPLOYED AI ENGINEERING

Capstone Project

Stage Four: Sprint Plan

Deciding who does what, in what order, and what finished means

A plan is not a list of tasks. It is a statement of sequence, ownership and
completion that the team has actually agreed to.

WEEK TWO · DAY ONE

How to plan three weeks of work

You have already lost a third of the project to discovery and requirements, which is as it should be. What remains has to be sequenced carefully, because several parts of the build depend on others and the dependencies are not always obvious until you hit them.

Figure 1. The shape of the three weeks, including the compulsory requirements revision.

Three rules that make the difference

Every item has an estimate in hours and a priority. When you run short of time, and you will, the priority column is what decides for you rather than whatever felt urgent that morning.

Every item has a definition of done written before work starts. Written afterwards, it describes whatever happened to be produced.

The retrieval layer and the evaluation harness come early, not late. Almost everything else depends on one or the other, and leaving the harness until the end means discovering your results too late to act on them.

The full unattended run over the hidden evaluation set happens in week two, not week three. It is the gate the project turns on, and it always exposes problems that never appear when you are testing one ticket at a time.

1   Section one: your capacity

Before you plan anything, work out honestly how much time you actually have. Plans built on optimistic capacity fail in week two rather than week three, which is worse, because by then you have committed to an architecture that assumed the time existed.

| Week | Hours realistically available | Other commitments that week | Days you cannot work |
| --- | --- | --- | --- |
| Week one (Wed 26 Aug - Sun 30 Aug) | 34.5h actual (per Effort Log Table 3) | Discovery + Requirements + ADRs + local env setup; individual project, single contributor. | None. Full week available. |
| Week two (Mon 31 Aug - Sun 6 Sep) | 40h planned | Build sprint. No competing commitments. Aim 8h/day Mon-Fri. | None planned. |
| Week three (Mon 7 Sep - Sat 13 Sep) | 35h planned | Governance + report + video + submission. Submit Sat 13 before 23:59 (time zone open per PRD Open Q4). | Buffer half day Sat 12 for last polish. |

On working alone Working individually removes the coordination overhead and replaces it with a different problem: nobody will notice when you have been stuck for six hours. Set yourself a rule that anything blocking you for more than an hour gets written down and either escalated or worked around, and check that list at the end of each day.

2   Section two: the backlog

List every item of work. Estimate in hours rather than in vague sizes, because hours can be compared against the capacity you recorded above. Mark dependencies explicitly, because the order matters more when there is only one of you.

| ID | Item | Est. hours | Priority | Depends on | Definition of done |
| --- | --- | --- | --- | --- | --- |
| B-01 | Environment + dependency setup on assessment-class machine | 3h (Wk1, done) | MUST | - | verify_setup PASS; python -m src.index_docs completes; SQLite decision log initialised. See Effort Log Table 3 rows for 30 Aug. |
| B-02 | Chroma index build over 29 KB articles (fixed 800/120 per D-04 provisional) | 1h (Wk1, done) | MUST | B-01 | storage/chroma populated; 59 passages indexed. Cites D-04 provisional; final ADR after B-07. |
| B-03 | PR-CLASSIFY-01 prompt (intent + urgency + calibrated confidence) | 2h | MUST | - | Prompt file in prompts/build/. Frontmatter: FR-04, FR-05. Three test cases (happy, injection, empty body) per capstone-prompt-writer skill. Registered in prompts/README.md. |
| B-04 | src/classify.py implementation | 3h | MUST | B-03 | ClassificationResult schema; fallback to unknown on provider failure (FR-05); no exception surfaces. Cites A3, A11. Companion pytest in tests/test_classify.py (happy, adversarial, degraded per capstone-test-writer skill). |
| B-05 | PR-RETRIEVE-01 optional query rewriting for the four low-hit intents | 2h | SHOULD (CUT 2026-09-02 — B-30 removed the underlying gap) | B-04, B-07 | CUT 2026-09-02. Was scoped for onboarding after B-07 showed hit@3 = 0.600 on that intent. After B-30 (title-prepending) onboarding hit@3 = 0.900 — no query rewriting needed. 2h saved. See workbooks/b30_findings.md. |
| B-06 | src/retrieve.py implementation | 3h | MUST | B-02 | Passage retrieval with resolvable doc_id + score; empty list on threshold miss (FR-07). Cites A4. Test fixture: query against fixed synthetic no-match returns []. |
| B-07 | D-02 revisit check: measure all-MiniLM-L6-v2 hit@3 vs TF-IDF 93.6% baseline | 1h | MUST | B-02 | evaluation/d02_retrieval_check.py runs; writes evaluation/results/d02_dense_retrieval.json. Verdict recorded in workbooks/d02_findings.md. Answers PRD Open Q1. |
| B-08 | D-04 chunking final ADR | 1h | MUST | B-07 | docs/adr/D-04-chunking.md written after dense-retrieval measurement. Either confirms fixed_800_120 or supersedes with a measured alternative. |
| B-09 | PR-GENERATE-01 prompt (grounded answer with citations) | 3h | MUST | B-06 | Prompt returns JSON {answer, citations[], confidence, unknown}. Injection separation via <<TICKET_START>>/<<TICKET_END>>. Cites FR-13, FR-15, A6, A7. Three test cases including injection attempt. |
| B-10 | PR-GENERATE-02 prompt (I-do-not-know response for empty retrieval) | 1h | MUST | B-06 | Prompt returns {unknown: true, citations: []}. Cites FR-14, EV-M3 (rather nothing than wrong). |
| B-11 | src/generate.py + inline Self-RAG groundedness check (D-06 pattern, retry cap 1) | 5h | MUST | B-09, B-10 | Generator returns validated JSON; groundedness critic verifies claims against retrieved passages; one retry on unsupported claim. Cites D-06, FR-13/14/17, A6/A7. Determinism preserved at temperature=0.0. |
| B-12 | PR-GUARDRAIL-PII-01 (block emails, keys, phone, account numbers, other customer names) | 2h | MUST | - | Prompt evaluates response for PII presence. Cites FR-16, R-02. Test case: crafted response with test@example.com triggers block=true. |
| B-13 | PR-GUARDRAIL-GROUNDING-01 (claim extraction + support verification) | 3h | MUST | B-09 | Prompt extracts factual claims, checks each against retrieved passages, returns list of unsupported claims. Cites FR-17, R-01. |
| B-14 | src/guardrails.py — all five guardrails blocking | 4h | MUST | B-12, B-13 | PII, grounding, instruction integrity, tone/scope, confidence floor. All blocking, none warning. Cites FR-15-19, A7. Test case per guardrail confirms block=True, blocking=True on triggering input. |
| B-15 | src/route.py — deterministic routing (auto_respond / escalate / block) | 3h | MUST | B-04, B-06, B-14 | Deterministic (FR-09); escalates on must_not_auto_respond or empty retrieval or guardrail block (FR-10); attaches EscalationBundle (FR-11); writes human-readable reason (FR-12). Cites A5. |
| B-16 | D-05 threshold sweep on validation set | 2h | MUST | B-04, B-15 | Sweep 0.5-0.95 in 0.05 steps; report auto-respond precision and recall per threshold; select value maximising FCR subject to precision >= 0.95. Writes docs/adr/D-05b.md. Answers PRD Open Q on threshold. |
| B-17 | PR-EVAL-JUDGE-01 (three-dim RAG rubric: context/grounded/answer relevance) | 3h | MUST | - | Judge prompt with position/verbosity/self-preference bias mitigations per capstone-prompt-writer skill. Judge model must be different family from generator. Cites NFR-01a/b/c. |
| B-18 | Judge calibration set: 50 hand-scored (ticket, response, passages) triples | 4h | SHOULD | B-17 | tests/fixtures/judge_calibration.json. Spearman >= 0.70 vs judge required to trust NFR-01b measurements. Cites capstone-test-writer skill. |
| B-19 | evaluation/harness.py — full end-to-end unattended run | 5h | MUST | B-04, B-06, B-11, B-14, B-15 | python -m evaluation.harness --input <path> --output <dir>. Processes every ticket, produces metrics_report.json + decision log; no manual intervention; single command per A9-A10. Cites FR-21, FR-22. |
| B-20 | pytest for each src component + guardrail block tests + injection tests | 4h | MUST | B-04, B-06, B-11, B-14, B-15 | python -m pytest tests/ -v passes green in CI in under 60s. Cites A12, FR-24, capstone-test-writer skill. |
| B-21 | Full validation set unattended run — Week 2 gate | 2h + waiting | MUST | B-19, B-20 | 80-ticket unattended run completes; metrics report present; decision log reconciles; no crashes. This is A9. Must clear by end of Week 2 per Build Spec section 5. |
| B-22 | PRD revision (Stage 5, compulsory) | 3h | MUST | B-21 | workbooks/Stage_5_PRD_Revision_Log.docx populated with what v1 got wrong, what changed, why. Requirements audit re-runs (traceability_audit.py) PASS. |
| B-23 | Governance framework fill: risk register full, fairness audit, incident procedure, kill switch | 5h | MUST | B-21 | workbooks/Governance_Framework.docx populated per pack template. Cites NFR-05 (fairness), EV-M5 (compliance). |
| B-24 | Fairness audit segment analysis over validation set results | 2h | MUST | B-21 | Segment rubric-scored quality by language_fluency, customer_tier, customer_region, channel. Assert no segment >15pp below best (NFR-05). |
| B-25 | Report writing (Stage 6 submission part 2) | 8h | MUST | B-21, B-22, B-23 | 20-30 page PDF per Submission Guide section order: executive summary through conclusions plus appendices. Ai-tool declaration included. |
| B-26 | Video recording v1 (rehearsal) + v2 (final) | 6h | MUST | B-21, B-25 | 20-minute recording covering: problem, discovery findings, system, live demonstration (success + escalation + guardrail block + gate run evidence), numbers, governance, next steps. MP4 1080p+. |
| B-27 | Submission packaging + final checklist | 2h | MUST | B-25, B-26 | FirstnameLastname_Capstone_Submission.zip with four folders (Video/Report/Workbooks/Source_Code). Uploaded before 13 Sep 23:59 (time zone: assumption; open Q4 in PRD). |
| B-28 | src/ingest.py implementation (FR-01 four-channel normalisation; FR-02 empty subject/body handling; FR-03 original_body/body split with cleaned text and warnings list). Discovered missing 2026-08-31 during B-04 — plan v1 skipped ingest as a numbered item. This is the correction. | 1.5h | MUST | - | src/ingest.py implements normalise_any(raw: dict) -> Ticket dispatching by channel; four per-channel normalisers; empty subject/body populate Ticket.warnings without raising; original_body preserved. Unit tests cover each channel, empty subject, empty body, unusual chars, and the FR-01 requirement to preserve customer segment fields on the Ticket for downstream router use. |
| B-29 | src/api.py implementation (FR-19 FastAPI POST /ticket endpoint; FR-20 healthz + Prometheus /metrics). Discovered missing 2026-08-31: plan v1 named every other component as a backlog item but not the API layer. Not strictly required by any A criterion (A9 covers the harness CLI, not HTTP), but the pack's Setup Guide and architecture assume it. | 1h | SHOULD | B-11, B-14, B-15 | src/api.py exposes POST /ticket accepting a raw ticket JSON, returning a routing decision + reply JSON. GET /healthz checks the model provider, Chroma, and SQLite are reachable. GET /metrics exposes Prometheus counters. Unit test covers the happy path plus a degraded (model unreachable) case; not required by the assessment gate. |
| B-30 | src/index_docs.py: prepend article title + category to each chunk before embedding. Discovered missing 2026-09-02 during code review — the biggest cheap lever on retrieval quality per EV-I2 (customer language vs article titles) was not being used. | 0.5h (done 2026-09-02) | MUST | B-02 | src/index_docs.py rebuilt to prepend '**<title>** (<category>)' before each chunk. Raw chunk preserved in metadata.chunk_text. store.persist() call removed (deprecated in chromadb 0.4.22). Re-measured d02_retrieval_check.py and recorded verdict in workbooks/b30_findings.md. Result: dense hit@3 91.0% -> 95.2%; onboarding hit@3 60% -> 90%; tier gap 8pp -> 1.4pp. Cascaded downstream updates: PRD NFR-01a v3, Open Q2 supersede, Open Q6 downgrade, B-05 cut, D-04 ADR now writable. |

3   Section three: the week two plan in detail

| Day | What will be finished by the end of the day | Hours | Risk to this |
| --- | --- | --- | --- |
| Monday 31 Aug | Sprint plan finalised. Git push + CI green after fixes (flake8 + Node 24 actions). B-07 D-02 revisit check run: dense hit@3 = 91.0%, D-02 stands. B-03 PR-CLASSIFY-01 drafted with three test cases; corrected to v1.1 after T-01 body verbatim fix and Input Scope section added; then v1.2 plain-language pass. Data Fidelity discipline added to capstone-conventions skill. Stage 5 PRD revision log rewritten from 4 non-substantive rows to 5 real v1→v2 requirement revisions + 7 assumptions + 3 held decisions. PRD bumped to v2 rolling. B-04 (src/classify.py) PULLED FORWARD from Tuesday: implemented with pluggable model call; 16 pytest cases pass; flake8 clean. Plan gap discovered: src/ingest.py wasn't scheduled — added as B-28 (see below). | ~14h actual | OVER BUDGET by ~6h. Discipline and rework overhead on documentation quality (revision log rewrite, plain-language pass) accounts for ~4h; pulling B-04 forward accounts for ~2h. Root cause: discovered mid-day that Stage 5 log entries didn't meet the pack's substantive-revision bar. Correction absorbed. |
| Tuesday 1 Sep | B-28 src/ingest.py + pytest green (1.5h; pulled in as morning task after yesterday's plan-gap discovery). B-06 src/retrieve.py + pytest green (2h). B-05 PR-RETRIEVE-01 written for onboarding only (per B-07 findings — 2h, SHOULD priority). B-04 was pulled to Monday evening; freed 3h for B-28 and buffer. | ~7h | B-28 estimate is honest but four-channel normalisers can surface edge cases not covered in the dev set (unusual chars). If ingest slips more than 30 min, defer B-05 to Wed AM — it's SHOULD not MUST. |
| Wednesday 2 Sep | B-30 (src/index_docs.py title-prepending) done in ~30 min and re-measured — dense hit@3 91.0% -> 95.2%, onboarding 60% -> 90%. Downstream: PRD NFR-01a v3 (hit@5 per-intent floor), Open Q2 answered (B-05 cut), Open Q6 downgraded, Stage 5 revision log entry, D-02 ADR strengthened, D-04 ADR (B-08) can now be written on the fuller picture. | ~2h so far today | Self-RAG retry loop debugging can spike; hard cap at 1 retry per D-06. |
| Thursday 3 Sep | B-11 generate finished + tests. B-12 PII guardrail prompt + fixture. B-13 grounding guardrail prompt. B-14 src/guardrails.py all five blocking. | 8h | Grounding guardrail's claim-extraction is the newest work; may need iteration. |
| Friday 4 Sep | B-15 src/route.py + tests. B-16 D-05 threshold sweep run + ADR. B-19 evaluation/harness.py end-to-end. B-21 first full validation unattended run — GATE. | 8h | This is the pack's Week 2 gate. If harness crashes mid-run, cut scope per Section 5 rather than defer gate to Week 3. |

4   Section four: the week three plan in detail

| Day | What will be finished by the end of the day | Hours | Risk to this |
| --- | --- | --- | --- |
| Monday 7 Sep | B-17 PR-EVAL-JUDGE-01 written. B-18 judge calibration set (50 hand-scored triples). Fix any issue exposed by B-21 gate run. | 8h | Judge calibration is 50 samples to hand-score; may spill into Tue if fatigue slows scoring. |
| Tuesday 8 Sep | B-22 PRD revision (Stage 5) drafted. B-23 governance framework populated part 1 (risk register full, incident procedure, kill switch). | 6h | Governance is the largest single Week 3 item; wants a full working session. |
| Wednesday 9 Sep | B-23 completed. B-24 fairness audit run + tabled. B-25 report writing sections 1-4 (Executive summary, problem, discovery, requirements). | 7h | None. |
| Thursday 10 Sep | B-25 report sections 5-10 (architecture, implementation, evaluation, governance, revision, conclusions) drafted. B-26 video v1 rehearsal recorded. | 6h | First video take always overruns per pack guidance; treat v1 as diagnostic not deliverable. |
| Friday 11 Sep | B-26 video v2 recorded and edited. B-27 submission packaging: rename archive, run pack's final checklist, dry-run clean-checkout install. | 5h | Save Sat 12 as buffer for anything found in the final checklist. |

5   Section five: what you will drop if you run out of time

You will run out of time. Every student does. Deciding now what gets cut is far better than deciding in a panic on the final Wednesday, and it protects the parts that carry the most marks.

| Item | Cut order | Consequence of cutting it | What you will say about it in the report |
| --- | --- | --- | --- |
| B-29 src/api.py (FastAPI + /healthz + /metrics endpoints) | 1st to go | No HTTP endpoint. Harness (evaluation/harness.py) still runs from the CLI, satisfies A9 unchanged. Marks assuming an API-first architecture would be lost. | src/api.py was scheduled as a SHOULD backlog item (B-29). Without it the system runs via the harness CLI, which is what the assessment gate uses. If time permits post-submission, the FastAPI wrapper is a straightforward addition. |
| B-05 PR-RETRIEVE-01 query rewriting for onboarding intent | CUT 2026-09-02 | No consequence — B-30 (title-prepending) took the onboarding intent from 60% to 90% hit@3, removing the need for query rewriting entirely. | PR-RETRIEVE-01 was not written. The problem it was designed to solve (onboarding retrieval below 75% hit@3 floor) no longer exists after B-30 improved onboarding to 90% hit@3. |
| B-18 judge calibration (50 hand-scored triples) | 3rd to go | Judge scores at face value; no human anchor. Threat to internal validity. | Judge calibration is called out in the evaluation section as a limitation; the three-dimensional rubric partly mitigates the concern. |
| Custom monitoring dashboards (Grafana) | 4th to go | Bare Prometheus /metrics endpoint satisfies A10; a Grafana dashboard is polish. Video demonstration uses metrics_report.json directly. | Prometheus /metrics is exposed; a Grafana dashboard would sit on top and is a Week-4 candidate. |
| Video v2 (second take) | 5th to go | Only cut if the day 10 v1 came out usable. Pack guidance is to record twice; skipping v2 costs some polish but preserves the gate. | Video is the single take; note that a second take would have tightened pacing. |

6   Section six: the daily check-in record

Ten minutes at the start of each day, answering the same three questions. Keeping this record is what makes your effort log accurate rather than reconstructed, and it is where you will notice a blocker that has quietly consumed two days.

| Date | Finished since yesterday | Doing today | Blocked by |
| --- | --- | --- | --- |
| 2026-08-31 (Mon) | Environment setup (B-01), Chroma index build (B-02), PR-CLASSIFY-01 drafted (B-03), capstone skills v1, five ADRs (D-01 through D-06), Stage 1 workbook, PRD v1, traceability_audit.py, sequencing-discipline skill update, effort log Wk1 populated. | Git push + CI green after ci.yml + eval-script flake8 fixes. B-07 D-02 revisit check run and findings written. Data Fidelity rule added to skill after PR-CLASSIFY-01 T-01 body paraphrase caught. Stage 5 revision log rewritten from 4 non-substantive rows to 5 real v1→v2 requirement revisions plus 7 assumptions plus 3 held decisions. PRD bumped to v2 rolling (FR-04 + NFR-01a + NFR-05 revised, FR-25 added, Open Q1/Q2 answered, Q6 raised). Plain-language pass across 8 artefacts. B-04 src/classify.py pulled forward from Tuesday and complete (16 pytest cases green). Plan gap discovered: ingest.py not on the plan — added as B-28. Sprint plan updated (this file). | None |
| 2026-09-01 (Tue) — planned | (fill Wed AM) | B-28 src/ingest.py implementation (morning). B-06 src/retrieve.py implementation. B-05 PR-RETRIEVE-01 written for onboarding only. Buffer time for any B-28 slippage. | - |
| 2026-09-02 (Wed) | B-08 D-04 final chunking ADR written (docs/adr/D-04-chunking.md). B-30 title+category prepending measured and applied to src/index_docs.py (workbooks/b30_findings.md). FR-25 removed after a Data Fidelity check during B-28 found 0 of 78 docs_comment tickets carry any article reference. NFR-01a revised to v3 on the B-30 evidence. | As left column. NOTE (entered retrospectively 2026-09-03 from artefact dates, not on the day): Table 4 scheduled B-09 and B-10 for this date. The day went to B-08, B-30 and the FR-25 data check instead; B-09 slipped to Thu 3 Sep and B-10 has not started. | None recorded. |
| 2026-09-03 (Thu) | B-06 review found a critical retrieval defect: the Chroma collection carried no hnsw:space, so LangChain scored with the l2 formula (1.0 - distance/sqrt(2)) on un-normalised MiniLM vectors, giving scores of -0.094 to 0.650. The uncalibrated 0.35 floor then cut hit@3 from 94.1% to 52.4%, leaving 151 of 357 answerable tickets with zero passages — NFR-01a's 90% floor missed by ~38pp. Cause was that the measurement (d02_retrieval_check.py) used similarity_search with no scores and no threshold, so it never covered the shipped path. Fixed as D-02a: cosine space, threshold 0.25 set by sweep; index rebuilt; hit@3 now 94.1% measured THROUGH retrieve(). Also in retrieve.py: A11 (malformed metadata no longer escapes), A6 (uncitable passages dropped), A8 (ticket_id now required), explicit sort, and a distance-space guard. B-28 rework: JSON null no longer becomes the string 'None', bare CR handled, unicode test de-fragilised; FR-01 revised to v2 (labels.* no longer required on the Ticket). D-03b written (decision-log write-failure policy). | B-09 closed: PR-GENERATE-01 rewritten v1.0.0 -> v2.0. The v1.0.0 draft was unloadable by src/prompt_loader.py (wrong section headings), used a schema that did not match FR-13 (missing 'confidence' entirely), cited filename/page fields the corpus does not have so every citation would have been fabricated, and named the wrong FRs. Five test cases now, four on verbatim dev tickets. B-10 NOT started. | PRD Table 9 Q7 — the FR-GUARD-01..04 scope decision. B-10's design depends on whether FR-GUARD-04 owns the low-retrieval-confidence case, so B-10 is held until Q7 is answered. |
| 2026-09-04 (Fri) |  |  |  |
| 2026-09-07 (Mon) |  |  |  |
| 2026-09-08 (Tue) |  |  |  |
| 2026-09-09 (Wed) |  |  |  |
| 2026-09-10 (Thu) |  |  |  |
| 2026-09-11 (Fri) |  |  |  |